## Burn down chart
Release Burndown
| Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
| 0 | 32 | 32
| 1 | 26 | 32
| 2 | 25 | 27
3
| 4 | 0
Sprint 1 Burndown
| Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
Thurs | 16 | 32 | 26
Fri | 15 |  | 26
Mon | 14 |  | 25
Tues | 13 |  | 25
Wed | 12 | 24 | 25
Thu | 11 |  | 25
Fri | 10 |  | 25
Mon | 9 |  | 24
Tues | 8 | 16 | 24
Wed | 7 |  | 23
Thu | 6 |  | 23
Fri | 5 |  | 23
Mon | 4 | 8 | 22
Tues | 3 |  | 22
Wed | 2 |  | 22
Thu | 1 |  | 22
Fri | 0 | 0 | 22
18 | Actual days
Sprint 2 Burndown
| Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
Tue | 18 | 22 | 22
Wed | 17 |  | 21
Thur | 16 |  | 21
Fri | 15 |  | 19
Mon | 14 |  | 17
Tue | 13 |  | 16
Wed | 12 | 14.6 | 15
Thur | 11 |  | 15
Fri | 10 |  | 14
Mon | 9 |  | 14
Tue | 8 |  | 14
Wed | 7 |  | 14
Thur | 6 | 7.3 | 13
Fri | 5 |  | 13
Mon | 4 |  | 12
Tue | 3 |  | 11
Wed | 2 |  | 10
Thur | 1 |  | 9
Fri - Submission | 0 | 0 | 9
A Key note from us (Group 92):
As a group we decided Unanimously that we should carry forward the previous stories and tasks. This is due to our group's performance in
the first sprint. The reason this occurred is due to some issues we faced as a group in regards to setting up the database and some overall
team member issues.On the other hand in regards to sprint 2, we finished with 9 tasks left. However, this one was out of our control as our
group was unable to implement it due to the Vehicle data that CRC provided us not including what we needed (inspection status). In relation
to days please refer to the velocity in Sprint and Release 1 and 2.